## STUDY
Task ID | Task | Details | Priority | Depends On | Status | Deliverable
T1 — Raspberry Pi
T1.1 | Study Raspberry Pi OS and initial setup | Learn OS flashing, SSH, basic config for RPi | High | - | done | 3
T1.2 | Study Docker and Docker Compose on RPi | Understand containerized deployment on ARM | High | T1.1 | done | 3
T2 — Node-RED
T2.1 | Study Node-RED flow-based programming | Understand nodes, flows, msg object, deploy model | High | - | done | 1, 3
T2.2 | Study node-red-contrib-modbus library | Learn Modbus read/write nodes, configuration | High | T2.1 | done | 1
T2.3 | Study Node-RED dashboard (v1 or FlowFuse v2) | Learn UI widgets: gauges, charts, buttons, tabs | Medium | T2.1 | done | 3
T3 — MQTT (Mosquitto)
T3.1 | Study MQTT protocol fundamentals | Publish/subscribe model, topics, QoS levels, retained messages | High | - | done | 1, 2
T3.2 | Study Eclipse Mosquitto broker configuration | Learn mosquitto.conf, authentication, logging | High | T3.1 | done | 1, 2, 3
T4 — ESP32 (WT32-ETH01)
T4.1 | Study WT32-ETH01 platform and LAN8720 Ethernet | Understand hardware, pinout, power requirements | High | - | done | 2
T4.2 | Study Arduino/PlatformIO setup for WT32-ETH01 | Board definitions, upload settings, libraries | High | T4.1 | done | 2
T4.3 | Study ESP32 Modbus TCP libraries (ModbusTCP) | Learn slave and master API implementation | High | T4.2 | done | 2
T4.4 | Study ESP32 MQTT client libraries | Learn PubSubClient or AsyncMQTT usage | Medium | T4.2 | done | 2
T5 — LOGO! PLC
T5.1 | Study LOGO! Soft Comfort programming environment | Learn FBD/Ladder programming, simulation, download | High | - | pending | 1
T5.2 | Study Modbus TCP protocol fundamentals | Master/slave architecture, registers, coils, function codes | High | - | done | 1, 2
T5.3 | Study LOGO! 8.4 Modbus TCP slave configuration | Register mapping, Ethernet setup, connection settings | High | T5.1 | done | 1
T5.4 | Study LOGO! 8.4 Modbus TCP master configuration | How LOGO! reads external slave devices | High | T5.3 | done | 1
T5.5 | Study LOGO! 8.4 native MQTT client configuration | Built-in MQTT topics for I/O publishing | Medium | T5.1 | Not Started | 1
T5.6 | Study LOGO! extension modules (DM8, DM16, AM2) | Understand digital/analog I/O expansion capabilities | High | T5.1 | Not Started | 1
T5.7 | Study relay board wiring with LOGO! outputs | Learn relay module interfacing for AC/DC load switching | High | T5.6 | Not Started | 1
T5.8 | Study I/O panel wiring and terminal connections | Input/output panel layout, wiring diagrams, terminal blocks | High | T5.6 | Not Started | 1
T6 — Grafana & InfluxDB
T6.1 | Study InfluxDB data model and queries | Measurements, tags, fields, retention policies, Flux/InfluxQL | Medium | - | done | 3
T6.2 | Study Grafana dashboard creation | Panels, data sources, queries, variables, alerts | Medium | T6.1 | done | 3
T7 — Samkoon HMI
T7.1 | Study Samkoon HMI programming software | Learn screen design, object placement, project structure | Medium | - | Not Started | 4
T7.2 | Study Samkoon HMI communication protocols | Confirm Modbus TCP support, connection parameters | High | T7.1 | Not Started | 4
T8 — Integration & Demo
T8.1 | Study water tank level control theory | On/off control, hysteresis, level sensing methods | Medium | - | Not Started | 1, 2, 3, 4

## RESEARCH
Task ID | Task | Details | Priority | Depends On | Status | Deliverable
T1 — Raspberry Pi
T1.3 | Research Raspberry Pi static IP and network topology | Plan IP addressing scheme for all devices on local network | High | T1.1 | Not Started | 1, 2, 3, 4
T2 — Node-RED
T2.4 | Research Node-RED dashboard options (v1 vs FlowFuse v2) | Compare features, community support, stability | Medium | T2.3 | Not Started | 3
T3 — MQTT (Mosquitto)
T3.3 | Research MQTT broker performance and reliability | Test message throughput, QoS impact, persistence | Low | T3.2 | Not Started | 1, 2, 3
T4 — ESP32 (WT32-ETH01)
T4.5 | Research WT32-ETH01 Ethernet initialization with LAN8720 | Verify library compatibility, known issues, GPIO config | High | T4.1 | Not Started | 2
T4.6 | Research ESP32 Modbus TCP library options | Compare ModbusTCP, eModbus, ArduinoModbus for master/slave | Medium | T4.3 | Not Started | 2
T5 — LOGO! PLC
T5.9 | Research LOGO! 8.4 Modbus TCP register address mapping | Identify I/O register addresses, data types, byte order | High | T5.3 | Not Started | 1
T5.10 | Research LOGO! as Modbus master capabilities and limitations | Less documented feature — test feasibility and constraints | High | T5.4 | Not Started | 1
T5.11 | Research LOGO! extension module addressing | How DM8/DM16/AM2 registers map in Modbus address space | High | T5.6 | Not Started | 1
T5.12 | Research relay board specifications for LOGO! outputs | Voltage/current ratings, coil voltage, contact type (NO/NC) | Medium | T5.7 | Not Started | 1
T5.13 | Research I/O panel component selection | Switches, indicators, terminal blocks, push buttons for demo panel | Medium | T5.8 | Not Started | 1
T6 — Grafana & InfluxDB
T6.3 | Research InfluxDB retention and downsampling policies | Plan storage strategy for long-term sensor data | Low | T6.1 | Not Started | 3
T7 — Samkoon HMI
T7.3 | Research Samkoon HMI Modbus TCP compatibility with LOGO! | Test if HMI can directly read LOGO! registers or needs gateway | High | T7.2 | Not Started | 4
T8 — Integration & Demo
T8.2 | Research water tank level sensor options | Ultrasonic, float switch, pressure transducer — select for demo | Medium | T8.1 | Not Started | 1, 2, 3, 4
T8.3 | Research PLC vs ESP32 performance comparison metrics | Define test procedures for response time comparison | Low | - | Not Started | 1, 2
T8.4 | Research Modbus TCP latency between all devices | Plan measurement method for Node-RED, LOGO!, ESP32 | Low | - | Not Started | 1, 2

## IMPLEMENT
Task ID | Task | Details | Priority | Depends On | Status | Deliverable
T1 — Raspberry Pi
T1.4 | Flash Raspberry Pi OS on RPi | Write OS image to SD card, configure SSH and Wi-Fi | High | - | done | 3
T1.5 | Install Docker and Docker Compose on RPi | Install container runtime and orchestration | High | T1.4 | done | 3
T1.6 | Assign static IPs to all devices | Configure RPi, LOGO!, ESP32, HMI on local network | High | T1.3, T1.4 | done | 1, 2, 3, 4
T2 — Node-RED
T2.5 | Deploy Node-RED in Docker with persistent volume | Docker container setup, port mapping, volume mount | High | T1.5 | done | 1, 3
T2.6 | Install node-red-contrib-modbus palette | Add Modbus TCP nodes to Node-RED | High | T2.5 | done | 1
T2.7 | Install node-red-dashboard palette | Add UI dashboard widgets | Medium | T2.5 | done | 3
T2.8 | Install node-red-contrib-influxdb palette | Add InfluxDB write/query nodes | Medium | T2.5 | Not Started | 3
T2.9 | Build flow: Modbus TCP master to poll LOGO! registers | Node-RED reads PLC I/O data via Modbus | High | T2.6, T5.15 | Not Started | 1
T2.10 | Build flow: Write to LOGO! coils via Modbus TCP | Node-RED as master controls PLC outputs | High | T2.9 | Not Started | 1
T2.11 | Build flow: MQTT subscribe to write to InfluxDB | Data pipeline from MQTT broker to database | Medium | T2.8, T3.4 | Not Started | 3
T2.12 | Build flow: MQTT subscribe to dashboard UI | Gauges, charts, buttons showing live data | Medium | T2.7, T3.4 | Not Started | 3
T2.13 | Build flow: Dashboard button to write Modbus register | UI control of PLC outputs via Node-RED | Medium | T2.10, T2.12 | Not Started | 1, 3
T3 — MQTT (Mosquitto)
T3.4 | Deploy Eclipse Mosquitto MQTT broker in Docker | Configure mosquitto.conf, ports, persistence | High | T1.5 | done | 1, 2, 3
T3.5 | Test MQTT pub/sub connectivity from all devices | Verify RPi, LOGO!, ESP32 can publish and subscribe | High | T3.4, T5.16, T4.11 | done | 1, 2
T4 — ESP32 (WT32-ETH01)
T4.7 | Set up Arduino/PlatformIO project for WT32-ETH01 | Board config, library dependencies, build verification | High | T4.2 | done | 2
T4.8 | Develop Ethernet initialization firmware | LAN8720 bring-up, static IP, network connectivity test | High | T4.5, T4.7 | done | 2
T4.9 | Develop ESP32 Modbus TCP slave implementation | Expose registers for PLC/Node-RED to read | High | T4.8 | Not Started | 2
T4.10 | Develop ESP32 Modbus TCP master implementation | Read LOGO! registers from ESP32 | High | T4.8 | Not Started | 2
T4.11 | Develop ESP32 MQTT client | Publish sensor data, subscribe to commands | Medium | T4.8, T3.4 | Not Started | 2
T4.12 | Interface sensors/actuators via I/O panel with ESP32 | Wire digital/analog I/O, test read/write | Medium | T4.8 | Not Started | 2
T4.13 | Test LOGO! reading ESP32 registers (LOGO! master, ESP32 slave) | Cross-device Modbus TCP integration | High | T4.9, T5.17 | Not Started | 1, 2
T4.14 | Test ESP32 reading LOGO! registers (ESP32 master, LOGO! slave) | Cross-device Modbus TCP integration | High | T4.10, T5.15 | Not Started | 1, 2
T5 — LOGO! PLC
T5.14 | Write LOGO! control program (FBD/Ladder) for pump start/stop | Program with I/O panel and extension module interaction | High | T5.1, T5.6 | done | 1
T5.15 | Configure LOGO! IP and enable Modbus TCP slave mode | PLC network and protocol setup | High | T5.3, T1.6 | done | 1
T5.16 | Configure LOGO! native MQTT client with topics for I/O | Set up MQTT publishing/subscribing from PLC | Medium | T5.5, T3.4 | Not Started | 1
T5.17 | Configure LOGO! as Modbus TCP master to read ESP32 slave | PLC reads ESP32 registers | High | T5.4, T4.9 | Not Started | 1
T5.18 | Wire relay board to LOGO! digital outputs | Connect relay module for AC/DC load switching (pump, valve) | High | T5.7, T5.14 | Not Started | 1
T5.19 | Wire I/O panel to LOGO! inputs and extension modules | Connect switches, indicators, push buttons, terminal blocks | High | T5.8, T5.14 | Not Started | 1
T5.20 | Test LOGO! extension module I/O via Modbus registers | Verify DM8/DM16/AM2 registers accessible via Modbus TCP | High | T5.11, T5.15 | Not Started | 1
T6 — Grafana & InfluxDB
T6.4 | Deploy InfluxDB in Docker | Configure database, retention policies, credentials | Medium | T1.5 | done | 3
T6.5 | Deploy Grafana in Docker | Configure and connect to InfluxDB data source | Medium | T6.4 | done | 3
T6.6 | Create Grafana dashboard for PLC I/O status | Stat panels for digital inputs/outputs from LOGO! and extensions | Medium | T6.5, T2.11 | Not Started | 3
T6.7 | Create Grafana time-series charts for sensor readings | Historical data visualization | Medium | T6.6 | Not Started | 3
T6.8 | Add Grafana alert rules (tank level high/low) | Automated alerting on thresholds | Low | T6.7 | Not Started | 3
T7 — Samkoon HMI
T7.4 | Configure Samkoon HMI to connect via Modbus TCP | HMI communication setup to LOGO! or Node-RED | Medium | T7.3, T5.15 | Not Started | 4
T7.5 | Design HMI screens: start/stop, status, analog values | HMI user interface for operator control | Medium | T7.4 | Not Started | 4
T7.6 | Test HMI reading live data from LOGO! | HMI integration and verification | Medium | T7.5 | Not Started | 4
T8 — Integration & Demo
T8.5 | Implement water tank level control: sensor to LOGO!/ESP32 | Demo application core control logic | High | T5.14, T4.12 | Not Started | 1, 2, 3, 4
T8.6 | Implement full data pipeline: sensor to MQTT to InfluxDB to Grafana | End-to-end data flow verification | High | T2.11, T6.5 | Not Started | 3
T8.7 | Demonstrate LOGO! as slave and master through Node-RED | Deliverable 1 proof — record/document results | High | T2.10, T5.17 | Not Started | 1
T8.8 | Run 24-hour continuous stability test | System reliability verification | Medium | T8.5, T8.6 | Not Started | 1, 2, 3, 4
T8.9 | Compare PLC vs ESP32 response time | Performance benchmarking for same control logic | Low | T8.5 | Not Started | 1, 2
T8.10 | Write final report and documentation | Project deliverable — all sections | High | T8.8 | Not Started | 1, 2, 3, 4

## LEGEND
PROJECT PLAN LEGEND
TASK GROUPS
T1 | Raspberry Pi
T2 | Node-RED
T3 | MQTT (Mosquitto)
T4 | ESP32 (WT32-ETH01)
T5 | LOGO! PLC
T6 | Grafana & InfluxDB
T7 | Samkoon HMI
T8 | Integration & Demo
PRIORITY LEVELS
High | Must complete — blocks other tasks or required for deliverables
Medium | Important but not blocking — can proceed in parallel
Low | Nice to have — complete if time allows
PROFESSOR'S 4 REQUIRED DELIVERABLES
1 | PLC (LOGO! 8.4) as Modbus TCP slave AND master through Node-RED
2 | ESP32 (WT32-ETH01) as Modbus TCP master/slave
3 | Visualize data on Grafana
4 | Visualize on Samkoon HMI
SHEET TYPES
STUDY | Learning, understanding protocols, reading docs, confirming specs
RESEARCH | Investigating feasibility, comparing options, testing, reading references
IMPLEMENT | Building, coding, deploying, configuring, integrating, testing